| WBS | Activity | Target Date | Status |
| --- | --- | --- | --- |
| 1 | Design & Architect the Platform | 9 Sept | Completed |
| 2 | Blockchain Network Structure | 11 Sept | Completed |
| 3 | Blockchain Network Implementation | 15 Sept | Completed |
| 4 | Blockchain Multi-Machine Setup | 17 Sept | Completed |
| 5 | Project Setup — NestJS + Next.js + RabbitMQ + Nginx | 21 Sep | Completed |
| 6 | Data Sources & Canonical Properties | 23 Sept | Completed |
| 7 | Design Ghost Beneficiary Detection Algorithm | 23 Sep | Completed |
| 8 | Implement Ghost Beneficiary Detection Algorithm | 25 Sep | Completed |
| 9 | Develop Screens for Ghost Beneficiary Detection | 28 Sep | Completed |
| 9.1 | Policy & Rules Setup | 28 Sep | Completed |
| 9.2 | Asynchronous Detection Job Scheduling | 29 Sep | Completed |
| 10 | Blockchain Gateway Setup | 30 Sep | Completed |
| 11 | Network Management UI & Contract Interaction Playground | 1 Oct | Completed |
| 12 | Application-Specific Blockchain Explorer Screens | 1 Oct | Completed |
| 13 | Develop & Deploy Chaincodes Related to Ghost Beneficiaries | 7 Oct 2026 | In Progress |
| 14 | Integration of Ghost Beneficiary Chaincodes | 8 Oct 2026 | In Progress |
| 15 | Ghost Beneficiary Investigation Case Registration & Workflow | 9 Oct 2026 | In Progress |
| 16 | Identity Management | 11 Oct 2026 |  |
| 17 | Internal Review and Bug Fixing | 14 Oct 2026 |  |
| 18 | Final Review | 15 Oct 2026 |  |